## Sheet1
Number | Start | End | Task | Notes
1 | 2022-01-10 | 2022-03-15 | literature review | ongoing / concurrent
2 | 2022-01-21 | 2022-01-27 | project proposal
3 | 2022-01-28 | 2022-02-04 | detection algorithm | Tasks conducted concurrently / iteratively |  | detection algorithm |  |  | ROS implementation | computer vision implementation
4 | 2022-02-05 | 2022-02-11 | distance calculation algorithm |  |  | distance calculation algorithm |  |  |  | motion control implementation
5 | 2022-02-12 | 2022-02-23 | vision implementation |  |  | vision implementation |  |  | CV algorithm | overhead camera / UAV
6 | 2022-02-24 | 2022-02-26 | motion implementation |  |  | motion implementaiton |  |  |  | floor camera
7 | 2022-02-27 | 2022-03-14 | software testing / algorithm revision |  |  | testing |  |  |  | computer vision algorithm
8 | 2022-03-15 | 2022-03-21 | prepare presenation |  |  | prepare presentation
9 | 2022-03-22 | 2022-04-14 | project + presentation complete |  |  | draft report
10 | 2022-04-01 | 2022-04-14 | draft report |  |  | edit
11 | 2022-04-14 | 2022-04-14 | submit report
[6 empty] | *everything in world frame |  |  | overhead cv
[6 empty] | *wafflebot has camera and will see turtlebot |  |  | detect turtlebot
[5 empty] | required nodes | subscribes to | task | published_topic | distinguish turtlebot from wafflebot
[5 empty] | vision_calculator | camera1, camera2, odom1, odom2 | calculates distances from imagery | object_position | determine direction to turtlbot from overhead camera
[5 empty] | robot_navigator | vision_calculator | publishes destination | destination | motion detection
[5 empty] | robot_driver | robot_navigator | sends velocity commands | cmd_vel
[5 empty] | cam1 | camera1 | records waffebot camera | camera1 | wafflebot camera
[5 empty] | cam2 | camera2 | records overhead camera | camera2 | determine direction to turtlbot from wafflebot
[5 empty] | rqt | built in node, no coding needed | move wafflebot